## Sheet1
ID | Task Name | Bucket Name | C3 | C4 | C5 | C6 | Created Date | C8 | C9 | C10 | Completed Date | C12 | C13 | C14 | C15 | Labels
1 | FMS Route Entry | Done |  |  |  |  | 02/19/2023 |  |  |  | 07/04/2023 |  |  |  |  | Arrival
2 | Altitude Constraint Logic | In Work |  |  |  |  | 02/07/2023 |  |  |  | 02/07/2023 |  |  |  |  | D&C
3 | Waypoint Validation | Review |  |  |  |  | 02/12/2023 |  |  |  | 02/12/2023 |  |  |  |  | HLTC
4 | Speed Profile Calc | Review |  |  |  |  | 02/24/2023 |  |  |  | 02/24/2023 |  |  |  |  | Airport
5 | Descent Path Optimization | Review |  |  |  |  | 01/31/2023 |  |  |  | 01/31/2023 |  |  |  |  | Airport
6 | Lateral Navigation Mode | Done |  |  |  |  | 04/22/2023 |  |  |  | 09/26/2023 |  |  |  |  | Arrival
7 | Vertical Navigation Mode | Review |  |  |  |  | 05/30/2023 |  |  |  | 05/30/2023 |  |  |  |  | LLTP
8 | Approach Procedure Loading | In Work |  |  |  |  | 01/17/2023 |  |  |  | 01/17/2023 |  |  |  |  | HLTP
9 | SID/STAR Processing | Review |  |  |  |  | 06/01/2023 |  |  |  | 06/01/2023 |  |  |  |  | LLTP
10 | Direct-To Function | Review |  |  |  |  | 04/12/2023 |  |  |  | 04/12/2023 |  |  |  |  | HLTP
11 | Hold Pattern Entry | Done |  |  |  |  | 03/31/2023 |  |  |  | 07/25/2023 |  |  |  |  | HLTC
12 | Offset Path Computation | In Work |  |  |  |  | 05/11/2023 |  |  |  | 05/11/2023 |  |  |  |  | D&C
13 | Weight & Balance Integration | In Work |  |  |  |  | 03/23/2023 |  |  |  | 03/23/2023 |  |  |  |  | Constraints
14 | Fuel Prediction Module | Done |  |  |  |  | 03/01/2023 |  |  |  | 07/13/2023 |  |  |  |  | HLTP
15 | Performance Init Page | Done |  |  |  |  | 04/01/2023 |  |  |  | 09/16/2023 |  |  |  |  | Constraints
16 | Takeoff Speeds Calc | In Work |  |  |  |  | 03/06/2023 |  |  |  | 03/06/2023 |  |  |  |  | HLTC
17 | Landing Speeds Calc | In Work |  |  |  |  | 04/20/2023 |  |  |  | 04/20/2023 |  |  |  |  | HLTC
18 | VNAV Path Construction | Review |  |  |  |  | 05/30/2023 |  |  |  | 05/30/2023 |  |  |  |  | D&C
19 | LNAV Sequencing | Done |  |  |  |  | 04/07/2023 |  |  |  | 08/15/2023 |  |  |  |  | D&C
20 | RNP AR Approach | In Work |  |  |  |  | 02/12/2023 |  |  |  | 02/12/2023 |  |  |  |  | Approach
21 | ILS Overlay Logic | Done |  |  |  |  | 04/03/2023 |  |  |  | 06/08/2023 |  |  |  |  | D&C
22 | GPS Position Update | In Work |  |  |  |  | 03/17/2023 |  |  |  | 03/17/2023 |  |  |  |  | Departure
23 | RAIM Monitoring | Review |  |  |  |  | 02/04/2023 |  |  |  | 02/04/2023 |  |  |  |  | HLTP
24 | ACARS Integration | Review |  |  |  |  | 05/19/2023 |  |  |  | 05/19/2023 |  |  |  |  | HLTP
25 | Datalink Message Handler | Done |  |  |  |  | 05/31/2023 |  |  |  | 09/11/2023 |  |  |  |  | HLTC
26 | Weather Uplink Processing | Done |  |  |  |  | 02/16/2023 |  |  |  | 08/08/2023 |  |  |  |  | Arrival
27 | ATIS Auto-Tune | In Work |  |  |  |  | 02/26/2023 |  |  |  | 02/26/2023 |  |  |  |  | LLTP
28 | Database Cycle Management | In Work |  |  |  |  | 05/30/2023 |  |  |  | 05/30/2023 |  |  |  |  | Departure
29 | Terrain Awareness Module | Done |  |  |  |  | 05/03/2023 |  |  |  | 07/01/2023 |  |  |  |  | Constraints
30 | GPWS Alerting Logic | In Work |  |  |  |  | 03/07/2023 |  |  |  | 03/07/2023 |  |  |  |  | LLTP
31 | TCAS Integration | Done |  |  |  |  | 04/27/2023 |  |  |  | 08/05/2023 |  |  |  |  | Arrival
32 | ADS-B Out Processing | Done |  |  |  |  | 05/27/2023 |  |  |  | 07/28/2023 |  |  |  |  | HLTP
33 | Transponder Mode Control | Done |  |  |  |  | 03/19/2023 |  |  |  | 05/20/2023 |  |  |  |  | HLTP
34 | Radio Frequency Mgmt | Done |  |  |  |  | 04/11/2023 |  |  |  | 04/21/2023 |  |  |  |  | Departure
35 | Navigation Display Rendering | In Work |  |  |  |  | 03/14/2023 |  |  |  | 03/14/2023 |  |  |  |  | Departure
36 | Primary Flight Display Logic | Done |  |  |  |  | 03/12/2023 |  |  |  | 03/18/2023 |  |  |  |  | HLTP
37 | Crew Alerting System | In Work |  |  |  |  | 01/30/2023 |  |  |  | 01/30/2023 |  |  |  |  | LLTC
38 | EICAS Message Priority | Done |  |  |  |  | 02/01/2023 |  |  |  | 09/25/2023 |  |  |  |  | D&C
39 | Maintenance Page Access | In Work |  |  |  |  | 04/09/2023 |  |  |  | 04/09/2023 |  |  |  |  | HLTP
40 | Built-In Test Equipment | Done |  |  |  |  | 05/26/2023 |  |  |  | 06/30/2023 |  |  |  |  | LLTP
41 | Software Loader Interface | Done |  |  |  |  | 05/19/2023 |  |  |  | 07/17/2023 |  |  |  |  | Constraints
42 | Config Data Validation | Done |  |  |  |  | 02/17/2023 |  |  |  | 08/26/2023 |  |  |  |  | Departure
43 | Memory Management Unit | In Work |  |  |  |  | 05/16/2023 |  |  |  | 05/16/2023 |  |  |  |  | LLTC
44 | I/O Bus Controller | Done |  |  |  |  | 05/16/2023 |  |  |  | 09/02/2023 |  |  |  |  | LLTC
45 | ARINC 429 Handler | In Work |  |  |  |  | 02/08/2023 |  |  |  | 02/08/2023 |  |  |  |  | HLTP
46 | MIL-STD-1553 Interface | In Work |  |  |  |  | 05/05/2023 |  |  |  | 05/05/2023 |  |  |  |  | Approach
47 | Ethernet Switch Config | Done |  |  |  |  | 05/03/2023 |  |  |  | 08/21/2023 |  |  |  |  | Arrival
48 | Power Management Logic | Done |  |  |  |  | 01/28/2023 |  |  |  | 07/24/2023 |  |  |  |  | HLTP
49 | Fault Isolation Procedure | Review |  |  |  |  | 01/30/2023 |  |  |  | 01/30/2023 |  |  |  |  | Airport
50 | Self-Test Sequence | Review |  |  |  |  | 04/11/2023 |  |  |  | 04/11/2023 |  |  |  |  | HLTP
51 | FMS Route Entry | Done |  |  |  |  | 03/19/2023 |  |  |  | 05/12/2023 |  |  |  |  | LLTC
52 | Altitude Constraint Logic | Done |  |  |  |  | 06/01/2023 |  |  |  | 08/02/2023 |  |  |  |  | HLTC
53 | Waypoint Validation | Done |  |  |  |  | 05/03/2023 |  |  |  | 06/23/2023 |  |  |  |  | LLTP
54 | Speed Profile Calc | Review |  |  |  |  | 05/13/2023 |  |  |  | 05/13/2023 |  |  |  |  | LLTC
55 | Descent Path Optimization | Done |  |  |  |  | 02/03/2023 |  |  |  | 06/01/2023 |  |  |  |  | Constraints
56 | Lateral Navigation Mode | Done |  |  |  |  | 02/09/2023 |  |  |  | 02/26/2023 |  |  |  |  | Constraints
57 | Vertical Navigation Mode | Review |  |  |  |  | 01/18/2023 |  |  |  | 01/18/2023 |  |  |  |  | HLTP
58 | Approach Procedure Loading | Done |  |  |  |  | 03/16/2023 |  |  |  | 05/02/2023 |  |  |  |  | Airport
59 | SID/STAR Processing | Done |  |  |  |  | 05/19/2023 |  |  |  | 09/24/2023 |  |  |  |  | LLTC
60 | Direct-To Function | Review |  |  |  |  | 04/27/2023 |  |  |  | 04/27/2023 |  |  |  |  | D&C
61 | Hold Pattern Entry | In Work |  |  |  |  | 02/26/2023 |  |  |  | 02/26/2023 |  |  |  |  | Airport
62 | Offset Path Computation | In Work |  |  |  |  | 01/15/2023 |  |  |  | 01/15/2023 |  |  |  |  | Airport
63 | Weight & Balance Integration | Done |  |  |  |  | 03/23/2023 |  |  |  | 07/22/2023 |  |  |  |  | LLTP
64 | Fuel Prediction Module | Done |  |  |  |  | 05/03/2023 |  |  |  | 09/27/2023 |  |  |  |  | Arrival
65 | Performance Init Page | Done |  |  |  |  | 02/23/2023 |  |  |  | 04/17/2023 |  |  |  |  | LLTP
66 | Takeoff Speeds Calc | Done |  |  |  |  | 03/11/2023 |  |  |  | 03/30/2023 |  |  |  |  | Departure
67 | Landing Speeds Calc | In Work |  |  |  |  | 01/30/2023 |  |  |  | 01/30/2023 |  |  |  |  | Approach
68 | VNAV Path Construction | Done |  |  |  |  | 01/29/2023 |  |  |  | 02/15/2023 |  |  |  |  | Departure
69 | LNAV Sequencing | Done |  |  |  |  | 05/17/2023 |  |  |  | 09/27/2023 |  |  |  |  | Constraints
70 | RNP AR Approach | Done |  |  |  |  | 02/24/2023 |  |  |  | 03/15/2023 |  |  |  |  | Constraints
71 | ILS Overlay Logic | Done |  |  |  |  | 02/04/2023 |  |  |  | 09/14/2023 |  |  |  |  | HLTC
72 | GPS Position Update | Done |  |  |  |  | 02/01/2023 |  |  |  | 07/08/2023 |  |  |  |  | HLTP
73 | RAIM Monitoring | Done |  |  |  |  | 03/16/2023 |  |  |  | 07/02/2023 |  |  |  |  | HLTP
74 | ACARS Integration | Done |  |  |  |  | 03/19/2023 |  |  |  | 08/19/2023 |  |  |  |  | Departure
75 | Datalink Message Handler | Done |  |  |  |  | 01/25/2023 |  |  |  | 07/07/2023 |  |  |  |  | HLTP
76 | Weather Uplink Processing | Review |  |  |  |  | 05/02/2023 |  |  |  | 05/02/2023 |  |  |  |  | Departure
77 | ATIS Auto-Tune | Review |  |  |  |  | 05/28/2023 |  |  |  | 05/28/2023 |  |  |  |  | Approach
78 | Database Cycle Management | Review |  |  |  |  | 03/22/2023 |  |  |  | 03/22/2023 |  |  |  |  | LLTC
79 | Terrain Awareness Module | Review |  |  |  |  | 04/05/2023 |  |  |  | 04/05/2023 |  |  |  |  | LLTC
80 | GPWS Alerting Logic | Done |  |  |  |  | 03/23/2023 |  |  |  | 07/07/2023 |  |  |  |  | HLTC
81 | TCAS Integration | In Work |  |  |  |  | 04/01/2023 |  |  |  | 04/01/2023 |  |  |  |  | Arrival
82 | ADS-B Out Processing | Done |  |  |  |  | 04/05/2023 |  |  |  | 04/28/2023 |  |  |  |  | D&C
83 | Transponder Mode Control | Review |  |  |  |  | 05/12/2023 |  |  |  | 05/12/2023 |  |  |  |  | Departure
84 | Radio Frequency Mgmt | Done |  |  |  |  | 02/09/2023 |  |  |  | 03/04/2023 |  |  |  |  | Constraints
85 | Navigation Display Rendering | Done |  |  |  |  | 03/10/2023 |  |  |  | 07/22/2023 |  |  |  |  | LLTP
86 | Primary Flight Display Logic | Review |  |  |  |  | 02/17/2023 |  |  |  | 02/17/2023 |  |  |  |  | Approach
87 | Crew Alerting System | Review |  |  |  |  | 02/01/2023 |  |  |  | 02/01/2023 |  |  |  |  | LLTC
88 | EICAS Message Priority | Done |  |  |  |  | 04/19/2023 |  |  |  | 07/05/2023 |  |  |  |  | HLTC
89 | Maintenance Page Access | Review |  |  |  |  | 05/07/2023 |  |  |  | 05/07/2023 |  |  |  |  | Constraints
90 | Built-In Test Equipment | Done |  |  |  |  | 04/02/2023 |  |  |  | 09/10/2023 |  |  |  |  | Constraints
91 | Software Loader Interface | Review |  |  |  |  | 01/17/2023 |  |  |  | 01/17/2023 |  |  |  |  | Constraints
92 | Config Data Validation | In Work |  |  |  |  | 04/01/2023 |  |  |  | 04/01/2023 |  |  |  |  | HLTP
93 | Memory Management Unit | In Work |  |  |  |  | 02/18/2023 |  |  |  | 02/18/2023 |  |  |  |  | LLTP
94 | I/O Bus Controller | Review |  |  |  |  | 02/13/2023 |  |  |  | 02/13/2023 |  |  |  |  | HLTP
95 | ARINC 429 Handler | Done |  |  |  |  | 02/23/2023 |  |  |  | 05/08/2023 |  |  |  |  | LLTP
96 | MIL-STD-1553 Interface | In Work |  |  |  |  | 03/09/2023 |  |  |  | 03/09/2023 |  |  |  |  | Approach
97 | Ethernet Switch Config | Review |  |  |  |  | 03/08/2023 |  |  |  | 03/08/2023 |  |  |  |  | LLTP
98 | Power Management Logic | In Work |  |  |  |  | 05/24/2023 |  |  |  | 05/24/2023 |  |  |  |  | Arrival
99 | Fault Isolation Procedure | In Work |  |  |  |  | 03/20/2023 |  |  |  | 03/20/2023 |  |  |  |  | D&C
100 | Self-Test Sequence | Done |  |  |  |  | 02/07/2023 |  |  |  | 07/24/2023 |  |  |  |  | Airport
101 | FMS Route Entry | Done |  |  |  |  | 03/26/2023 |  |  |  | 04/11/2023 |  |  |  |  | D&C
102 | Altitude Constraint Logic | Review |  |  |  |  | 04/10/2023 |  |  |  | 04/10/2023 |  |  |  |  | HLTC
103 | Waypoint Validation | Review |  |  |  |  | 03/23/2023 |  |  |  | 03/23/2023 |  |  |  |  | HLTC
104 | Speed Profile Calc | Done |  |  |  |  | 05/08/2023 |  |  |  | 08/30/2023 |  |  |  |  | Constraints
105 | Descent Path Optimization | Done |  |  |  |  | 01/17/2023 |  |  |  | 02/19/2023 |  |  |  |  | HLTP
106 | Lateral Navigation Mode | In Work |  |  |  |  | 02/22/2023 |  |  |  | 02/22/2023 |  |  |  |  | Constraints
107 | Vertical Navigation Mode | Done |  |  |  |  | 01/24/2023 |  |  |  | 08/30/2023 |  |  |  |  | Approach
108 | Approach Procedure Loading | In Work |  |  |  |  | 02/21/2023 |  |  |  | 02/21/2023 |  |  |  |  | Airport
109 | SID/STAR Processing | Review |  |  |  |  | 02/16/2023 |  |  |  | 02/16/2023 |  |  |  |  | D&C
110 | Direct-To Function | In Work |  |  |  |  | 04/03/2023 |  |  |  | 04/03/2023 |  |  |  |  | Approach
111 | Hold Pattern Entry | Done |  |  |  |  | 01/25/2023 |  |  |  | 09/17/2023 |  |  |  |  | Approach
112 | Offset Path Computation | Review |  |  |  |  | 03/09/2023 |  |  |  | 03/09/2023 |  |  |  |  | LLTC
113 | Weight & Balance Integration | Done |  |  |  |  | 02/10/2023 |  |  |  | 05/16/2023 |  |  |  |  | Constraints
114 | Fuel Prediction Module | Done |  |  |  |  | 04/29/2023 |  |  |  | 06/12/2023 |  |  |  |  | LLTC
115 | Performance Init Page | Done |  |  |  |  | 02/25/2023 |  |  |  | 09/22/2023 |  |  |  |  | HLTC
116 | Takeoff Speeds Calc | Done |  |  |  |  | 04/30/2023 |  |  |  | 05/11/2023 |  |  |  |  | HLTC
117 | Landing Speeds Calc | Review |  |  |  |  | 04/10/2023 |  |  |  | 04/10/2023 |  |  |  |  | Airport
118 | VNAV Path Construction | Done |  |  |  |  | 03/19/2023 |  |  |  | 05/31/2023 |  |  |  |  | HLTC
119 | LNAV Sequencing | Done |  |  |  |  | 02/11/2023 |  |  |  | 05/24/2023 |  |  |  |  | D&C
120 | RNP AR Approach | In Work |  |  |  |  | 05/15/2023 |  |  |  | 05/15/2023 |  |  |  |  | LLTC
121 | ILS Overlay Logic | Done |  |  |  |  | 03/07/2023 |  |  |  | 07/07/2023 |  |  |  |  | Approach
122 | GPS Position Update | In Work |  |  |  |  | 04/03/2023 |  |  |  | 04/03/2023 |  |  |  |  | LLTC
123 | RAIM Monitoring | Review |  |  |  |  | 03/13/2023 |  |  |  | 03/13/2023 |  |  |  |  | D&C
124 | ACARS Integration | Review |  |  |  |  | 03/05/2023 |  |  |  | 03/05/2023 |  |  |  |  | Airport
125 | Datalink Message Handler | Review |  |  |  |  | 04/09/2023 |  |  |  | 04/09/2023 |  |  |  |  | LLTP
126 | Weather Uplink Processing | Done |  |  |  |  | 02/01/2023 |  |  |  | 08/22/2023 |  |  |  |  | LLTP
127 | ATIS Auto-Tune | Review |  |  |  |  | 04/14/2023 |  |  |  | 04/14/2023 |  |  |  |  | Constraints
128 | Database Cycle Management | In Work |  |  |  |  | 04/27/2023 |  |  |  | 04/27/2023 |  |  |  |  | Constraints
129 | Terrain Awareness Module | Review |  |  |  |  | 04/09/2023 |  |  |  | 04/09/2023 |  |  |  |  | D&C
130 | GPWS Alerting Logic | Review |  |  |  |  | 02/13/2023 |  |  |  | 02/13/2023 |  |  |  |  | LLTP
131 | TCAS Integration | Done |  |  |  |  | 03/01/2023 |  |  |  | 08/01/2023 |  |  |  |  | LLTP
132 | ADS-B Out Processing | In Work |  |  |  |  | 01/24/2023 |  |  |  | 01/24/2023 |  |  |  |  | HLTP
133 | Transponder Mode Control | In Work |  |  |  |  | 05/06/2023 |  |  |  | 05/06/2023 |  |  |  |  | Approach
134 | Radio Frequency Mgmt | Done |  |  |  |  | 04/05/2023 |  |  |  | 07/30/2023 |  |  |  |  | Departure
135 | Navigation Display Rendering | Done |  |  |  |  | 05/25/2023 |  |  |  | 06/13/2023 |  |  |  |  | Airport
136 | Primary Flight Display Logic | In Work |  |  |  |  | 03/04/2023 |  |  |  | 03/04/2023 |  |  |  |  | LLTP
137 | Crew Alerting System | In Work |  |  |  |  | 01/26/2023 |  |  |  | 01/26/2023 |  |  |  |  | Airport
138 | EICAS Message Priority | Review |  |  |  |  | 01/15/2023 |  |  |  | 01/15/2023 |  |  |  |  | Constraints
139 | Maintenance Page Access | Done |  |  |  |  | 06/01/2023 |  |  |  | 09/01/2023 |  |  |  |  | LLTC
140 | Built-In Test Equipment | In Work |  |  |  |  | 04/18/2023 |  |  |  | 04/18/2023 |  |  |  |  | Airport
141 | Software Loader Interface | Done |  |  |  |  | 02/01/2023 |  |  |  | 07/26/2023 |  |  |  |  | Approach
142 | Config Data Validation | In Work |  |  |  |  | 04/05/2023 |  |  |  | 04/05/2023 |  |  |  |  | HLTP
143 | Memory Management Unit | Review |  |  |  |  | 04/01/2023 |  |  |  | 04/01/2023 |  |  |  |  | Constraints
144 | I/O Bus Controller | Review |  |  |  |  | 04/04/2023 |  |  |  | 04/04/2023 |  |  |  |  | Airport
145 | ARINC 429 Handler | Done |  |  |  |  | 04/08/2023 |  |  |  | 07/25/2023 |  |  |  |  | LLTP
146 | MIL-STD-1553 Interface | Done |  |  |  |  | 02/16/2023 |  |  |  | 04/11/2023 |  |  |  |  | Airport
147 | Ethernet Switch Config | In Work |  |  |  |  | 04/22/2023 |  |  |  | 04/22/2023 |  |  |  |  | HLTC
148 | Power Management Logic | In Work |  |  |  |  | 04/02/2023 |  |  |  | 04/02/2023 |  |  |  |  | Airport
149 | Fault Isolation Procedure | Done |  |  |  |  | 01/15/2023 |  |  |  | 04/07/2023 |  |  |  |  | LLTP
150 | Self-Test Sequence | In Work |  |  |  |  | 03/09/2023 |  |  |  | 03/09/2023 |  |  |  |  | Airport