## Sheet1
Task Name | C1 | Bucket Name | C3 | C4 | C5 | C6 | C7 | C8 | Due Date | C10 | C11 | C12 | C13 | C14 | C15 | Labels | Current Date
FMS Route Entry |  | Development | [6 empty] | 07/29/23 | [6 empty] | Arrival | 02/19/23
FMS Route Entry |  | Done | [6 empty] | 07/29/23 | [6 empty] | Arrival | 08/30/23
Altitude Constraint Logic |  | Development | [6 empty] | 05/06/23 | [6 empty] | Constraints | 04/01/23
Altitude Constraint Logic |  | Done | [6 empty] | 05/06/23 | [6 empty] | Constraints | 06/19/23
Waypoint Validation |  | Development | [6 empty] | 06/03/23 | [6 empty] | LLTC | 02/21/23
Waypoint Validation |  | Done | [6 empty] | 06/03/23 | [6 empty] | LLTC | 04/27/23
Speed Profile Calc |  | Development | [6 empty] | 09/01/23 | [6 empty] | HLTC | 02/22/23
Speed Profile Calc |  | Done | [6 empty] | 09/01/23 | [6 empty] | HLTC | 03/04/23
Descent Path Optimization |  | Development | [6 empty] | 02/21/23 | [6 empty] | Constraints | 01/31/23
Descent Path Optimization |  | Done | [6 empty] | 02/21/23 | [6 empty] | Constraints | 04/18/23
Lateral Navigation Mode |  | Development | [6 empty] | 09/30/23 | [6 empty] | D&C | 03/26/23
Lateral Navigation Mode |  | Done | [6 empty] | 09/30/23 | [6 empty] | D&C | 06/15/23
Vertical Navigation Mode |  | Development | [6 empty] | 05/12/23 | [6 empty] | HLTC | 04/06/23
Vertical Navigation Mode |  | Done | [6 empty] | 05/12/23 | [6 empty] | HLTC | 08/16/23
Approach Procedure Loading |  | Development | [6 empty] | 08/06/23 | [6 empty] | D&C | 03/29/23
Approach Procedure Loading |  | Done | [6 empty] | 08/06/23 | [6 empty] | D&C | 06/16/23
SID/STAR Processing |  | Development | [6 empty] | 05/08/23 | [6 empty] | Arrival | 03/12/23
SID/STAR Processing |  | Done | [6 empty] | 05/08/23 | [6 empty] | Arrival | 06/14/23
Direct-To Function |  | Development | [6 empty] | 03/27/23 | [6 empty] | D&C | 02/16/23
Direct-To Function |  | Done | [6 empty] | 03/27/23 | [6 empty] | D&C | 06/25/23
Hold Pattern Entry |  | Development | [6 empty] | 04/04/23 | [6 empty] | HLTP | 03/07/23
Hold Pattern Entry |  | Done | [6 empty] | 04/04/23 | [6 empty] | HLTP | 07/17/23
Offset Path Computation |  | Development | [6 empty] | 05/23/23 | [6 empty] | Departure | 04/05/23
Offset Path Computation |  | Done | [6 empty] | 05/23/23 | [6 empty] | Departure | 04/25/23
Weight & Balance Integration |  | Development | [6 empty] | 07/24/23 | [6 empty] | HLTC | 04/28/23
Weight & Balance Integration |  | Done | [6 empty] | 07/24/23 | [6 empty] | HLTC | 09/26/23
Fuel Prediction Module |  | Development | [6 empty] | 07/17/23 | [6 empty] | HLTP | 02/15/23
Fuel Prediction Module |  | Done | [6 empty] | 07/17/23 | [6 empty] | HLTP | 03/24/23
Performance Init Page |  | Development | [6 empty] | 09/17/23 | [6 empty] | Airport | 04/02/23
Performance Init Page |  | Done | [6 empty] | 09/17/23 | [6 empty] | Airport | 09/08/23
Takeoff Speeds Calc |  | Development | [6 empty] | 08/09/23 | [6 empty] | LLTC | 04/24/23
Takeoff Speeds Calc |  | Done | [6 empty] | 08/09/23 | [6 empty] | LLTC | 09/11/23
Landing Speeds Calc |  | Development | [6 empty] | 08/19/23 | [6 empty] | Arrival | 03/12/23
Landing Speeds Calc |  | Done | [6 empty] | 08/19/23 | [6 empty] | Arrival | 06/03/23
VNAV Path Construction |  | Development | [6 empty] | 08/10/23 | [6 empty] | Airport | 02/23/23
VNAV Path Construction |  | Done | [6 empty] | 08/10/23 | [6 empty] | Airport | 07/25/23
LNAV Sequencing |  | Development | [6 empty] | 06/05/23 | [6 empty] | D&C | 04/03/23
LNAV Sequencing |  | Done | [6 empty] | 06/05/23 | [6 empty] | D&C | 05/05/23
RNP AR Approach |  | Development | [6 empty] | 03/19/23 | [6 empty] | LLTC | 02/17/23
RNP AR Approach |  | Done | [6 empty] | 03/19/23 | [6 empty] | LLTC | 08/12/23
ILS Overlay Logic |  | Development | [6 empty] | 07/15/23 | [6 empty] | HLTC | 02/14/23
ILS Overlay Logic |  | Done | [6 empty] | 07/15/23 | [6 empty] | HLTC | 04/06/23
GPS Position Update |  | Development | [6 empty] | 05/29/23 | [6 empty] | HLTP | 02/04/23
GPS Position Update |  | Done | [6 empty] | 05/29/23 | [6 empty] | HLTP | 02/11/23
RAIM Monitoring |  | Development | [6 empty] | 08/21/23 | [6 empty] | Arrival | 04/13/23
RAIM Monitoring |  | Done | [6 empty] | 08/21/23 | [6 empty] | Arrival | 09/19/23
ACARS Integration |  | Development | [6 empty] | 06/25/23 | [6 empty] | LLTP | 01/19/23
ACARS Integration |  | Done | [6 empty] | 06/25/23 | [6 empty] | LLTP | 03/26/23
Datalink Message Handler |  | Development | [6 empty] | 05/12/23 | [6 empty] | LLTP | 04/14/23
Datalink Message Handler |  | Done | [6 empty] | 05/12/23 | [6 empty] | LLTP | 08/15/23
Weather Uplink Processing |  | Development | [6 empty] | 09/17/23 | [6 empty] | LLTC | 02/17/23
Weather Uplink Processing |  | Done | [6 empty] | 09/17/23 | [6 empty] | LLTC | 09/13/23
ATIS Auto-Tune |  | Development | [6 empty] | 08/05/23 | [6 empty] | Departure | 04/09/23
ATIS Auto-Tune |  | Done | [6 empty] | 08/05/23 | [6 empty] | Departure | 06/05/23
Database Cycle Management |  | Development | [6 empty] | 09/16/23 | [6 empty] | HLTP | 03/25/23
Database Cycle Management |  | Done | [6 empty] | 09/16/23 | [6 empty] | HLTP | 05/28/23
Terrain Awareness Module |  | Development | [6 empty] | 04/05/23 | [6 empty] | HLTC | 02/18/23
Terrain Awareness Module |  | Done | [6 empty] | 04/05/23 | [6 empty] | HLTC | 09/24/23
GPWS Alerting Logic |  | Development | [6 empty] | 07/08/23 | [6 empty] | HLTP | 01/22/23
GPWS Alerting Logic |  | Done | [6 empty] | 07/08/23 | [6 empty] | HLTP | 03/12/23
TCAS Integration |  | Development | [6 empty] | 07/12/23 | [6 empty] | Departure | 04/20/23
TCAS Integration |  | Done | [6 empty] | 07/12/23 | [6 empty] | Departure | 09/19/23
ADS-B Out Processing |  | Development | [6 empty] | 08/04/23 | [6 empty] | Arrival | 01/30/23
ADS-B Out Processing |  | Done | [6 empty] | 08/04/23 | [6 empty] | Arrival | 06/05/23
Transponder Mode Control |  | Development | [6 empty] | 07/02/23 | [6 empty] | LLTP | 04/14/23
Transponder Mode Control |  | Done | [6 empty] | 07/02/23 | [6 empty] | LLTP | 08/02/23
Radio Frequency Mgmt |  | Development | [6 empty] | 07/25/23 | [6 empty] | Constraints | 03/25/23
Radio Frequency Mgmt |  | Done | [6 empty] | 07/25/23 | [6 empty] | Constraints | 08/05/23
Navigation Display Rendering |  | Development | [6 empty] | 07/30/23 | [6 empty] | HLTP | 04/01/23
Navigation Display Rendering |  | Done | [6 empty] | 07/30/23 | [6 empty] | HLTP | 04/18/23
Primary Flight Display Logic |  | Development | [6 empty] | 04/18/23 | [6 empty] | Approach | 04/02/23
Primary Flight Display Logic |  | Done | [6 empty] | 04/18/23 | [6 empty] | Approach | 06/12/23
Crew Alerting System |  | Development | [6 empty] | 09/25/23 | [6 empty] | HLTP | 02/13/23
Crew Alerting System |  | Done | [6 empty] | 09/25/23 | [6 empty] | HLTP | 08/11/23
EICAS Message Priority |  | Development | [6 empty] | 09/29/23 | [6 empty] | Departure | 03/31/23
EICAS Message Priority |  | Done | [6 empty] | 09/29/23 | [6 empty] | Departure | 04/12/23
Maintenance Page Access |  | Development | [6 empty] | 05/22/23 | [6 empty] | LLTP | 03/29/23
Maintenance Page Access |  | Done | [6 empty] | 05/22/23 | [6 empty] | LLTP | 04/15/23
Built-In Test Equipment |  | Development | [6 empty] | 07/23/23 | [6 empty] | Arrival | 03/22/23
Built-In Test Equipment |  | Done | [6 empty] | 07/23/23 | [6 empty] | Arrival | 09/11/23
Software Loader Interface |  | Development | [6 empty] | 06/08/23 | [6 empty] | LLTP | 02/07/23
Software Loader Interface |  | Done | [6 empty] | 06/08/23 | [6 empty] | LLTP | 07/13/23
Config Data Validation |  | Development | [6 empty] | 05/05/23 | [6 empty] | Arrival | 01/26/23
Config Data Validation |  | Done | [6 empty] | 05/05/23 | [6 empty] | Arrival | 06/02/23
Memory Management Unit |  | Development | [6 empty] | 08/26/23 | [6 empty] | Airport | 02/26/23
Memory Management Unit |  | Done | [6 empty] | 08/26/23 | [6 empty] | Airport | 05/26/23
I/O Bus Controller |  | Development | [6 empty] | 05/30/23 | [6 empty] | HLTP | 02/04/23
I/O Bus Controller |  | Done | [6 empty] | 05/30/23 | [6 empty] | HLTP | 05/06/23
ARINC 429 Handler |  | Development | [6 empty] | 06/12/23 | [6 empty] | Arrival | 02/20/23
ARINC 429 Handler |  | Done | [6 empty] | 06/12/23 | [6 empty] | Arrival | 08/15/23
MIL-STD-1553 Interface |  | Development | [6 empty] | 03/15/23 | [6 empty] | Constraints | 01/19/23
MIL-STD-1553 Interface |  | Done | [6 empty] | 03/15/23 | [6 empty] | Constraints | 05/22/23
Ethernet Switch Config |  | Development | [6 empty] | 03/27/23 | [6 empty] | Approach | 02/16/23
Ethernet Switch Config |  | Done | [6 empty] | 03/27/23 | [6 empty] | Approach | 05/16/23
Power Management Logic |  | Development | [6 empty] | 09/15/23 | [6 empty] | Airport | 03/21/23
Power Management Logic |  | Done | [6 empty] | 09/15/23 | [6 empty] | Airport | 03/28/23
Fault Isolation Procedure |  | Development | [6 empty] | 04/07/23 | [6 empty] | Constraints | 03/15/23
Fault Isolation Procedure |  | Done | [6 empty] | 04/07/23 | [6 empty] | Constraints | 07/05/23
Self-Test Sequence |  | Development | [6 empty] | 09/07/23 | [6 empty] | LLTC | 03/22/23
Self-Test Sequence |  | Done | [6 empty] | 09/07/23 | [6 empty] | LLTC | 06/29/23
FMS Route Entry v2 |  | Testing | [6 empty] | 07/14/23 | [6 empty] | Arrival | 10/01/23
Altitude Constraint Logic v2 |  | Testing | [6 empty] | 03/28/23 | [6 empty] | D&C | 10/01/23
Waypoint Validation v2 |  | Testing | [6 empty] | 03/09/23 | [6 empty] | Constraints | 10/01/23
Speed Profile Calc v2 |  | Testing | [6 empty] | 09/17/23 | [6 empty] | Arrival | 10/01/23
Descent Path Optimization v2 |  | Review | [6 empty] | 02/11/23 | [6 empty] | HLTP | 10/01/23
Lateral Navigation Mode v2 |  | Review | [6 empty] | 04/24/23 | [6 empty] | HLTC | 10/01/23
Vertical Navigation Mode v2 |  | Review | [6 empty] | 05/19/23 | [6 empty] | Constraints | 10/01/23
Approach Procedure Loading v2 |  | Review | [6 empty] | 09/07/23 | [6 empty] | LLTC | 10/01/23
SID/STAR Processing v2 |  | Review | [6 empty] | 03/06/23 | [6 empty] | Arrival | 10/01/23
Direct-To Function v2 |  | Testing | [6 empty] | 09/30/23 | [6 empty] | Arrival | 10/01/23
Hold Pattern Entry v2 |  | Testing | [6 empty] | 08/03/23 | [6 empty] | Constraints | 10/01/23
Offset Path Computation v2 |  | Testing | [6 empty] | 09/05/23 | [6 empty] | Airport | 10/01/23
Weight & Balance Integration v2 |  | Testing | [6 empty] | 04/07/23 | [6 empty] | Arrival | 10/01/23
Fuel Prediction Module v2 |  | Testing | [6 empty] | 03/13/23 | [6 empty] | Constraints | 10/01/23
Performance Init Page v2 |  | Review | [6 empty] | 09/27/23 | [6 empty] | LLTC | 10/01/23
Takeoff Speeds Calc v2 |  | Testing | [6 empty] | 04/15/23 | [6 empty] | HLTP | 10/01/23
Landing Speeds Calc v2 |  | Testing | [6 empty] | 08/24/23 | [6 empty] | Approach | 10/01/23
VNAV Path Construction v2 |  | Testing | [6 empty] | 04/17/23 | [6 empty] | D&C | 10/01/23
LNAV Sequencing v2 |  | Testing | [6 empty] | 07/02/23 | [6 empty] | Departure | 10/01/23
RNP AR Approach v2 |  | Testing | [6 empty] | 05/29/23 | [6 empty] | HLTC | 10/01/23
ILS Overlay Logic v2 |  | Testing | [6 empty] | 04/30/23 | [6 empty] | Approach | 10/01/23
GPS Position Update v2 |  | Testing | [6 empty] | 09/30/23 | [6 empty] | Arrival | 10/01/23
RAIM Monitoring v2 |  | Review | [6 empty] | 08/01/23 | [6 empty] | LLTC | 10/01/23
ACARS Integration v2 |  | Review | [6 empty] | 05/13/23 | [6 empty] | Departure | 10/01/23
Datalink Message Handler v2 |  | Testing | [6 empty] | 02/15/23 | [6 empty] | Airport | 10/01/23
Weather Uplink Processing v2 |  | Testing | [6 empty] | 08/03/23 | [6 empty] | Arrival | 10/01/23
ATIS Auto-Tune v2 |  | Review | [6 empty] | 07/23/23 | [6 empty] | Airport | 10/01/23
Database Cycle Management v2 |  | Review | [6 empty] | 02/13/23 | [6 empty] | Arrival | 10/01/23
Terrain Awareness Module v2 |  | Testing | [6 empty] | 07/05/23 | [6 empty] | Constraints | 10/01/23
GPWS Alerting Logic v2 |  | Testing | [6 empty] | 09/15/23 | [6 empty] | HLTP | 10/01/23
TCAS Integration v2 |  | Testing | [6 empty] | 06/18/23 | [6 empty] | HLTP | 10/01/23
ADS-B Out Processing v2 |  | Review | [6 empty] | 08/07/23 | [6 empty] | D&C | 10/01/23
Transponder Mode Control v2 |  | Review | [6 empty] | 09/14/23 | [6 empty] | Airport | 10/01/23
Radio Frequency Mgmt v2 |  | Testing | [6 empty] | 06/04/23 | [6 empty] | HLTP | 10/01/23
Navigation Display Rendering v2 |  | Testing | [6 empty] | 07/13/23 | [6 empty] | Approach | 10/01/23
Primary Flight Display Logic v2 |  | Testing | [6 empty] | 09/10/23 | [6 empty] | HLTP | 10/01/23
Crew Alerting System v2 |  | Testing | [6 empty] | 05/12/23 | [6 empty] | Constraints | 10/01/23
EICAS Message Priority v2 |  | Review | [6 empty] | 09/15/23 | [6 empty] | Arrival | 10/01/23
Maintenance Page Access v2 |  | Review | [6 empty] | 02/21/23 | [6 empty] | Departure | 10/01/23
Built-In Test Equipment v2 |  | Review | [6 empty] | 04/03/23 | [6 empty] | LLTP | 10/01/23
Software Loader Interface v2 |  | Review | [6 empty] | 03/01/23 | [6 empty] | Airport | 10/01/23
Config Data Validation v2 |  | Testing | [6 empty] | 03/18/23 | [6 empty] | Arrival | 10/01/23
Memory Management Unit v2 |  | Testing | [6 empty] | 02/15/23 | [6 empty] | D&C | 10/01/23
I/O Bus Controller v2 |  | Testing | [6 empty] | 04/20/23 | [6 empty] | D&C | 10/01/23
ARINC 429 Handler v2 |  | Review | [6 empty] | 05/25/23 | [6 empty] | Approach | 10/01/23
MIL-STD-1553 Interface v2 |  | Testing | [6 empty] | 06/19/23 | [6 empty] | LLTC | 10/01/23
Ethernet Switch Config v2 |  | Review | [6 empty] | 07/28/23 | [6 empty] | Departure | 10/01/23
Power Management Logic v2 |  | Review | [6 empty] | 03/20/23 | [6 empty] | HLTC | 10/01/23
Fault Isolation Procedure v2 |  | Testing | [6 empty] | 09/14/23 | [6 empty] | Departure | 10/01/23
Self-Test Sequence v2 |  | Review | [6 empty] | 07/28/23 | [6 empty] | Departure | 10/01/23